## Sheet1
Your Project Name Here
Overall | Project Overview - Provide an overview of your project. This should be similar to the project description in the project charter. | [6 empty] | Project Type |  | Blue Chip
Schedule | [7 empty] | OCIO Senior Leader |  | Helen Patton
Budget | [7 empty] | Project Director |  | Mike Hiatt
Resources | [7 empty] | Project Manager |  | Lisa Dumont
Scope | [7 empty] | Date Range |  | 11/7/13 - 12/6/13
Risk
Executive Summary - Summary of the current project status. Include any significant milestones met, new issues, etc. For any non-green status areas, include reason for non-green status and brief description of how you plan to get it back to green. All data in fields below if for sample purposes only. Please replace with your own project information.
Key Accomplishments |  |  |  |  | Key Tasks / Milestones |  |  |  | Start | Finish | Status
ASC - Deployed to Production |  |  |  |  | FCOB (Fisher College of Business) - Completed |  |  |  | 2013-07-01 | 2013-07-29 | Completed
ASC - Held Lessons Learned meeting |  |  |  |  | ASC - Go Live |  |  |  | 2013-11-20 | 2013-11-26 | Completed
BFAP - Completed development and testing |  |  |  |  | ASC - Lessons Learned |  |  |  | 2013-12-05 | 2013-12-05 | Completed
Med Ctr - Outlined high level schedule |  |  |  |  | ASC - 2nd Lessons Learned |  |  |  | 2014-01-31 | 2014-01-31 | Not started
Med Ctr - Began Requirements / Attributes |  |  |  |  | MED CTR - Project Authorization |  |  |  | 2013-08-23 | 2013-10-05 | Completed
Next Steps |  |  |  |  | MED CTR - Planning Meeting |  |  |  | 2013-11-14 | 2013-11-14 | Completed
ASC - Schedule 2nd Lesson Learned meeting |  |  |  |  | MED CTR - High Level Schedule |  |  |  | 2013-12-03 | 2013-12-03 | Completed
ASC - Work with them to draft communications for non-IT rollout |  |  |  |  | MED CTR - Requirements & Design |  |  |  | 2013-11-14 | 2013-12-16 | In progress
BFAP - Get CAB approval for deployment |  |  |  |  | MED CTR - Development |  |  |  | 2013-12-16 | 2014-01-31 | Not started
BFAP - Deploy to Production |  |  |  |  | MED CTR - Testing |  |  |  | 2014-01-31 | 2014-02-15 | Not started
Med Ctr - Re-align with Med Ctr on scope issue |  |  |  |  | MED CTR - Firewall rules deadline |  |  |  | 2014-02-04 | 2014-02-04 | Not started
Critical Issues |  |  |  | Response | MED CTR - Major change deadline |  |  |  | 2014-02-11 | 2014-02-11 | Not started
Go Live issue - Network routing issues between the database network where IdM sits and the AD Domain controller which Arts and Sciences maintains. |  |  |  | Resolved | MED CTR - Go Live |  |  |  | 2014-02-28 | 2014-02-28 | Not started
[5 empty] | BFAP (Business, Finance, & Admin Planning) engagement |  |  |  | 2013-09-12 | 2013-09-27 | Completed
[5 empty] | BFAP - Kickoff Meeting |  |  |  | 2013-10-23 | 2013-10-23 | Completed
Med Ctr Bi-directional password sync confusion - believing they will be able to change passwords & synchronized back to OCIO IDM. Discussions have always been OCIO IDM system being the “center” of the Identity universe usingr my.osu.edu to change passwords & IDM distributing that password to all connected systems involved across the entire university |  |  |  | Investigating | BFAP - Requirements & Design |  |  |  | 2013-10-28 | 2013-11-08 | Completed
[5 empty] | BFAP - Dev & Testing |  |  |  | 2013-11-09 | 2013-12-10 | Completed
[5 empty] | BFAP - Change to go to the OCIO Change Advisory Board |  |  |  | 2013-12-10 | 2013-12-10 | In progress
[5 empty] | BFAP - Go Live Date |  |  |  | 2013-12-18 | 2013-12-18 | Not started
[5 empty] | BFAP - Lessons Learned |  |  |  | TBD | TBD | Not started
[5 empty] | Student Life - engagement |  |  |  | 2014-03-11 | 2014-03-14 | Not started
[5 empty] | Student Life - Target Kickoff Meeting (not finalized) |  |  |  | TBD | 2014-03-31 | Not started
Critical Risks |  |  |  | Response | Student Life - Target Go Live Date (not finalized) |  |  |  | TBD | 2014-05-28 | Not started
None to report at this time |  |  |  | N/A | Project Completed |  |  |  | 2014-06-30 | 2014-06-30 | Not started
Dollars vs. Hours | Actuals | ETC (Estimate to Complete) | EAC (Estimate at Complete) | Budget | Variance $ | Variance % | Financial Comments
Hours | 344 | 1656 | 0 | 2000 | 0 | 0% | as os 12/6/13
Dollars | 0 | 0 | 0 | 0 | 0 | 0% | Financials in progress